Lusaka and Chongwe Early Childhood Development Program

Activities to accelerate implementation of the program

27 October – 4 November 2025, Lusaka

1. Introduction

Early childhood is a critical period in terms of a child’s cognitive, emotional and physical development, with profound implications for lifelong learning and wellbeing. Early childhood development (ECD) represents a vital investment in health, education and economic productivity, laying the groundwork for lasting wellbeing and community resilience.

Successful ECD starts long before birth, with the education and health of caregivers and mothers. Investing in ECD and nutrition early on tends to improve lifelong health prospects, and so diminishes the risk of illness, stunting and malnourishment. Early interventions – such as improved access to pre-primary education, quality health services, community empowerment and sectoral reforms – lead to better academic performance as well as improved social and emotional skills in children.

In Zambia, His Excellency, the President of the Republic of Zambia, Mr Hakainde Hichilema, has committed to “ensuring that children are raised in a better society…into a responsible citizen” by prioritising early and foundational years and rolling out a multisectoral approach to ECD.

The Mayors of Lusaka and Chongwe Districts in Zambia have committed to making their cities welcoming, hospitable, and thriving environments for children. With the ambition of providing a safe and nurturing environment that fosters children developmental outcomes, the leadership of the two Districts seek to deliver an integrated Early Childhood Development (ECD) program that ensures children under 6 years in Lusaka and Chongwe are developmentally on track in health, nutrition, learning and social-emotional wellbeing. This program aims to build on and leverage the progress made by the Government of Zambia in strengthening the provision of ECD services and strengthening multisectoral ECD governance.

2. Program ambition

The transformative goal of the program is to ensure 95% of the 747,800 children under six years in Lusaka and Chongwe are developmentally on track in health, learning and socio-emotional wellbeing by 2030.

3. Strategic pillars

To deliver on this transformative goal, five key strategic pillars have been prioritised:

- Parental coaching on nurturing care: Promote nurturing among parents and caregivers of children under five through parental coaching programs within health centres, households, communities and workplaces.

- Quality and stimulating childcare services: Promote equitable access to quality and stimulating childcare services for children aged 0-3 years.

- Improved nutrition and stunting reduction: Ensure children under six years have access to nutritious and balanced meals for improved nutrition and reduction in stunting.

- Play-based learning in pre-primary schools: Ensure children aged 3-5 have equitable access to quality integrated play-based learning for improved school readiness.

- Outdoor play spaces: Create opportunities for outdoor play in communal spaces.

4. Baseline study on state of ECD in Lusaka and Chongwe

These strategic initiatives were prioritised based on the findings from a baseline study commissioned to assess early childhood development outcomes in Lusaka and Chongwe. The baseline study found:

- Concerningly, almost 1 in 2 (46%) children aged 0–3 years in Lusaka and Chongwe districts are developmentally off track. This is nine times greater than the global average of 5%.

- Early stimulation through responsive caregiving is limited in both Lusaka and Chongwe, with national values around nurturing care often not passed from generation to generation.

- Household access to social protection services is around 10 times higher in planned settlements compared to unplanned settlements. This increases a child’s risk of exposure to psychological aggression and physical punishment.

- 3 in 10 children aged five are stunted. Although similar to national prevalence (32%), this is unacceptably high for urban centres.

- Less than 1 in 10 caregivers in Lusaka and Chongwe use available play facilities and green spaces on a regular basis. This prevents children from interacting with and learning from the outdoor environment to support their development.

- Two-thirds of children in Lusaka and three-quarters in Chongwe fail to meet school readiness benchmarks.

- The Government of Zambia has made great strides in developing a multisectoral ECD framework. However, ECD implementation could be improved through strengthened coordination and, where appropriate, the standardisation of service delivery.

5. Activities to accelerate implementation of priority program activities

To transition into program implementation, key strategic activities have been prioritized for the period October to December 2025. To accelerate the implementation of these initial priority activities, Lusaka City Council and Chongwe Municipal Council are planning a series of program convenings.

Modality: the activities will be undertaken in up to five distinct convenings. Multi-day convenings will run in parallel in one location in Lusaka over the course of the visit. Groups should be no larger than 12 people to ensure focused and strategic discussions and be guided by two expert facilitators per group.

The objectives and key activities for the convening, structured by strategic pillar, are as follows:

Group 1: Parental coaching on nurturing care. Promote nurturing among parents and caregivers of children under five through parental coaching programs within health centres, households, communities and workplaces.

Objective 1: Mainstream ECD in all five Maternal, Newborn and Child Health (MNCH) touch points in health centres.

Key activities:

- Finalize strategy for mainstreaming ECD in MNCH touch points (definition, overview, targets)

- Review and adopt Care for Child Development Framework

- Review and adapt Care for Child Development training materials (manuals, resources, guides, displays)

- Develop an implementation plan for parental coaching services

- Develop a system for tracking and monitoring program performance – indicators, systems, tools.

Participants:

- Facilitator: Ministry of Health (ECD Focal Point)

- Health specialists from Lusaka City Council

- Health specialists from Chongwe Municipal Council

- Other Ministry of Health representatives

- District Health Boards/Officers

- Development partners involved in health centre service delivery

- Reputable local NGOs

Objective 2: Promote the provision of nurturing care amongst parents and caregivers through parental coaching in households, communities and workplaces.

Key activities:

- Finalize strategy for mainstreaming parental coaching services (definition, overview, targets)

- Review and adopt existing framework for parental coaching program

- Adopt harmonized parental coaching training materials (manuals, resources, guides, displays)

- Develop an implementation plan for parental coaching services

- Develop a system for tracking and monitoring program performance – indicators, systems, tools.

Participants:

- Health specialists from Lusaka City Council

- Health specialists from Chongwe Municipal Council

- Ministry of Community Development (ECD Focal Point)

- Other Ministry of Community Development representatives

- Ministry of Health representatives

- District Health Boards/Officers

- Development partners involved in ECD and parental coaching service delivery

- Reputable local NGOs

Group 2: Quality and stimulating childcare services. Promote equitable access to quality and stimulating childcare services for children aged 0-3 years.

Objective 3: Ensure the provision of quality, stimulating and nurturing childcare services across all service providers in Lusaka and Chongwe.

Key activities:

- Finalize strategy for the provision of quality and stimulating childcare services (definition, overview, targets)

- Review existing childcare models being delivered in Lusaka and Chongwe and, where necessary, adapt to best practice

- Review and adopt childcare worker curriculum training materials (manuals, resources, guides, displays)

- Develop an implementation plan for quality and stimulating childcare services

- Develop a system for tracking and monitoring program performance – indicators, systems, tools.

Participants:

- Facilitator: Ministry of Community Development (ECD Focal Point)

- Education specialists from Lusaka City Council

- Education specialists from Chongwe Municipal Council

- Other Ministry of Community Development representatives

- Ministry of Education representatives

- District Education Boards/Officers

- Development partners involved in childcare provision

- Reputable local NGOs

Group 3: Play-based learning in pre-primary schools. Ensure children aged 3-5 have equitable access to quality integrated play-based learning for improved school readiness.

Objective 4: Develop and adopt a harmonized approach to play-based learning in all Early Childhood Centres.

Key activities:

- Finalize strategy for developing and adopting a harmonized approach to play-based learning in all Education Childhood Centers (definition, overview, targets)

- Review existing play-based training materials and adopt a harmonized training framework

- Develop an implementation plan for play-based learning

- Develop a system for tracking and monitoring program performance – indicators, systems, tools

Participants:

- Facilitator: Ministry of Education (ECD Focal Point)

- Education specialists from Lusaka City Council

- Education specialists from Chongwe Municipal Council

- Other Ministry of Education representatives

- District Education Boards/Officers

- Development partners involved in ECE centres and pre-primary education

- Reputable local NGOs

Group 4: Outdoor play spaces. Create opportunities for outdoor play in communal spaces.

Objective 5: Promote learn through play through the creation of safe, age-appropriate play facilities in outdoor communal spaces.

Key activities:

- Finalize strategy for promoting learning through play through the creation of safe, age-appropriate play facilities in outdoor communal spaces.

- Review and adopt appropriate designs for safe, age-appropriate play facilities

- Review and identify priority sites for safe, age-appropriate play facilities

- Develop an implementation plan to promote learn through play (including the construction, management, operations and safety of outdoor play facilities)

- Develop a system for tracking and monitoring program performance – indicators, systems, tools

Participants:

- Engineering and Housing specialists from Lusaka City Council

- Engineering and Housing specialists from Chongwe Municipal Council

- Ministry of Education representatives

- Development partners involved in outdoor play facility provision (e.g. Slumdwellers International)

- Reputable local NGOs