PROMOTING PLAY-BASED LEARNING IN ECD CENTERS IN LUSAKA

Implementation Plan

| Transformative goal for the program for play-based learning | - To capacity build teachers to be confident and effective in delivering quality ECCDE services - To help learners, achieve their developmental domains holistically using best practices of how they want to learn (Play based) - To make ECCDE centres learner attractive as purposeful and organized play is the focus of all activities |
| --- | --- |
| Which ECE workers need their capacity built | - Teachers - Parents - Caregivers (assistant teachers) - School leaders - Community leaders (civic leaders, traditional leaders and the clergy) - Health practitioners - Law enforcement officers |
| How do we identify the workers? | - The multi-sectoral cluster, will dictate the operationisation of the trainees |
| Who is responsible for training these ECE workers? | - Using the multi-sectoral structure at district the following will roll out the trainings: - Ministry of Education (Directorates of: ECE, TESS, CDC) - Ministry of Health (Maternal Child Health Unit, Nutrition Dept.) - Ministry of Community Development and Social Services (Child Development Dept.) - Ministry of Home Affairs and Internal Security (Victim Support Unit) |
| What play-based learning components will they be trained on | - Play Based Curriculum – Play based pedagogy - PCC Manual - Orientation on the Parent Centre Committee - Manual on Positive Parenting - Positive Parenting and Play - School Readiness Tool - School Readiness - Caregivers Manual - Child Safeguard and Protection - Caregivers Manual - Child Health and Nutrition - Raising Star/Learning Roots Manuals - Home learning and Play - ECAT – Early Childhood Assessment Tool. |
| What materials will be used to train them | - Orientation on the Parent Centre Committee (PCC) - Positive Parenting and Play - School Readiness - Child Safeguard and Protection - Child Health and Nutrition - Home learning and Play |
| How many ECE workers will be trained (Lusaka and Chongwe) | 1 Lusaka – 170 - Teachers - 70 - Parents - 30 - Caregivers (assistant teachers) - 20 - School leaders - 10 - Community leaders (civic leaders, traditional leaders and the clergy) - 10 - Health practitioners - 10 - Law enforcement officers – 10 - Civil Society - 10 2 Chongwe – 155 - Teachers - 50 - Parents - 20 - Caregivers (assistant teachers) - 30 - School leaders - 20 - Community leaders (civic leaders, traditional leaders and the clergy) - 20 - Health practitioners - 5 - Law enforcement officers – 5 - Civil Society - 5 |
| Monitoring approach and tools | Monitoring - The convener’s (councils) will use the MoE, Monitoring and Evaluation tools to monitor both training and implementation - Administrative gap…… - Personnel identification…. - Skill requisites - The training teams will also use the already established mechanisms embedded in the programme and apply the tools designed for quality assurance in the system Tools - Formative Assessment Tool – FAT - Early Childhood Assessment Tool - ECAT - M & E training tool |
| Quality assurance approach and tools | - Centres and proprietors to be oriented in the National Quality Standards of Early Childhood Education (NQS) - Quality Early Learning Environment and Resources Tool (QELER) - Early Learning Development Standards (ELDS) - School Readiness Assessment Tool (SRAT) |
| How do we integrate into existing systems for Lusaka and Chongwe | - The two councils of Lusaka and Chongwe should make themselves visible to the District Education Office so as to be included in the many capacity building activities currently running for schools through the Continuing Professional Development (CPD) programme. - Assign officers to manage the CPD coordination at centre level. (School based in-house training, Cluster training, Zonal and Resource Centre designed programmes) - SPRINT – School Programme for In-service for the Term) |