## Parent Coaching (hidden)
Lusaka and Chongwe Early Childhood Development Program
Monitoring Framework for the Parent Coaching Program
| Indicator definition | Indicator Type (Output/Outcome) | Indicator calculation | Target | Who Collects Person Responsible | Medium of Collection (Tool) | Frequency | Disaggregation | Data Utilisation
1 | Number of households in which parents and caregivers with children under 5 years receive ECD parent coaching visits | Output, | Number of households visited | Target for number of households visits per month |  |  |  | Number of parents and caregivers coached Number of vulnerable households reached Number of children whose parents and caregivers receive parent coaching wards
2 | Number of parents and caregivers with children under 5 years receive who participate in group parent coaching sessiosn | Output, | Number of households visited | Target for number of households visits per month |  |  |  | Number of vulnerable households reached Number of children whose parents and caregivers receive parent coaching Wards
3 | Number of children assessed for development milestones | Outcome | No. of children under 5 years assessed (numerator) over Number of children under 5 years | Target for number of children to be assessed
5 | Number of children under 5 years with delayed developmental milestones referred. | Outcome | No. of children under 5 years assessed for delayed developmental milestones referred (numerator) over No. of children under 5 years assessed (denominator) | Target number of children assessed for delayed developmental milestones
6 | Number of children referred for Malnutrition | Outcome | No. of children under 5 years assessed for malnutrition referred (numerator) over total No. of children under 5 years assessed (denominator) | Target number of children with Malnutrition
7 | Number of children under 5 years of age with appropriate play items | Outcome | Number of children under 5 years of age with appropriate play items | Target number of children under 5 years visited
8 | Number of immunization defaulters referred | Outcome | Number of immunization defaulters referred | Target number of immunization defaulters identified.
9 | Number of children referred for childhood illnesses | Outcome | Number of children referred for childhood illnesses | Target number of children with childhood illnesses
10 | Current Number of pregnant women | Outcome | Current Number of pregnant women | Target number of current pregnant women
11 | Number of pregnant women referred for new ANC | Outcome | Number of pregnant women referred for new ANC | Target number of new pregnant women identified
12 | Number of pregnant women referred for missed ANC | Outcome | Number of pregnant women referred for missed ANC | Target number of pregnant women who missed ANC
Behaviour Change
13a | Number of parents | Outcome | A parent showing positive parental practice is someone with a "2" score against each high impact parental practice (talk/sing to child, play with child, tell stories/read to child, plays outdoors with child and respons to child's needs). This indicator is a) the number of parents with a score of "2" against each and | Target number of parents/caregivers against target as percentage |  |  | Monthly | Sub-County/County | Sub-County/County
13b | Number of parents | Outcome | b) the number of parents/caregivers that previously did NOT score "2" against each who this period scored "2" for each parental practice. | Target number of parents/caregivers against target as percentage |  |  | Monthly | Sub-County/County | Sub-County/County
Advocacy and Communication(Demand creation)
14 | Number of NCfECD community dialogue days held | Provision of service | Number of community dialogue days held | Quarterly community dialogue days held |  |  | Quarterly | Sub-County/County | Sub-County/County
15 | Number of people participated in the community dialogue days. | Outcome | Number of people participated in the community dialogue days. | Number of people participated in the community dialogue days. |  |  | Quarterly | Sub-County/County | Sub-County/County
16 | Number of NCfECD community action days held | Provision of service | Number of community action days held | Monthly community action days. |  |  | Monthly | Sub-County/County | Sub-County/County
17 | Number of people participated in the community action days | Outcome | Number of people participated in the community action days | Number of people participated in the community action days |  |  | Monthly | Sub-County/County | Sub-County/County
Monitoring and Evaluation
18 | Number of NCfECD supportive supervisions conducted | Provision of service | Number of NCfECD supportive supervisions conducted | Quarterly supportive supervisions. |  |  | Quarterly | Sub-County/County | Sub-County/County
19 | Number of NCfECD data review meeting conducted | Provision of service | Number of NCfECD data review meeting conducted | Quarterly data review meeting. |  |  | Quarterly | Sub-County/County | Sub-County/County
Note on I8: Geraldine Munn-Mace: I think it’s important to keep how many children are assessed for developmental milestones
Note on J8: Geraldine Munn-Mace: I think it’s important to keep how many children are assessed for developmental milestones
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There would not be a target of children with malnutrition. The target would be the number of children assessed
Note on I18: Geraldine Munn-Mace: I think it is important to monitor behaviour change of parents through the five high impact parental practices
Note on J18: Geraldine Munn-Mace: I think it is important to monitor behaviour change of parents through the five high impact parental practices

## Monitoring Framework
Lusaka and Chongwe Early Childhood Development Program
Monitoring Framework for the Parent Coaching Program
| Indicator definition | Indicator Type (Output/Outcome) | Indicator calculation | Target | Who Collects Person Responsible | Medium of Collection (Tool) | Frequency | Disaggregation | Data Utilisation
1 | Number of households in which parents and caregivers with children under 5 years receive ECD parent coaching visits | Output, | Number of households visited | Target for number of households visits per month |  |  |  | Number of parents and caregivers coached Number of vulnerable households reached Number of children whose parents and caregivers receive parent coaching wards
2 | Number of parents and caregivers with children under 5 years receive who participate in group parent coaching sessiosn | Output, | Number of households visited | Target for number of households visits per month |  |  |  | Number of vulnerable households reached Number of children whose parents and caregivers receive parent coaching Wards
3
5
6
7
8
9
Note on I8: Geraldine Munn-Mace: I think it’s important to keep how many children are assessed for developmental milestones
Note on J8: Geraldine Munn-Mace: I think it’s important to keep how many children are assessed for developmental milestones
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There would not be a target of children with malnutrition. The target would be the number of children assessed

## Workplan
Lusaka and Chongwe Early Childhood Development Program Initiative
Implementation Workplan - Initiative 1 - Provision of Nurturing Care through Parent Coaching Program
Key Activities | Milestones | Timelines | [7 empty] | Key Dates | Person Responsible | Rating (RAG)
|  | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | Q2 - 2026 | Q3 - 2026 | Q4 - 2026
Material Development
Finalie the training materials (ECD Family Counselling cards, Group Counselling Cards, Facilitators Manaual, Participants Manual, Cards)
Reproduction of training materials
Community Engagement and Sensitization
Orientation workshop with Ward Councillors and Ward Development Committees | Understanding of their role and responsibilities in the parent coaching program and solicit their support in the utilisation of CDF in support of ECD activities This orientation should involve all the other ECD program components A one-day orientation workshop
Hold Community Sensitization meetings using public announcement system and theatre development | Create awareness and expectation of the program among community members, parents and caregivers use community radio stations, and other channels of engagement to create aawareness about the program
Parent Coaches and Supervisors Training
Develop a training schedule or plan for rollout | participants, training schedule, agenda, etc
Conduct a resource preparatory session for parent coaching and supervisor training | A 2-3 day preparatory workshop on TOT for parent coaching and supervision Complete plannign session for the TOT training an average of 1000 coaches to be trained by 14 facilitators in 25 sessions
Conduct a train of trainer (TOT) session | Conduct TOT session for 20 people and select 14 facilitators through a validation exercise
Training of parent coaches | 8-10 day training including field visits for 1000 parent coaches and xxx supervisors Supervisors are mandated to attend the parent coach training
Training of Supervisors of parent coaches | A 3-day supervisor training
Conduct of Parent Coaching at Household
Assign parent coaches to teams, supervisors and catchment areas | Liaise with the MOH to identify catchment areas and assign coaches accordingly
Parent coaches conduct their first home visits, secure consent and enlistment (gather basic information on households) | Each parent coach should have 30 - 50 households to visit and coach
Parent coaches conduct home visits | Parent coaches conduct home visits in accordance with the visiting protocols Parent coaches to coach parents, gather basic information on the caregiver
Parent coach to conduct milestone assessment and parenting behaviour data | Tool to be developed
Conduct of Parent Coaching at Group Level
Identify targeted places for group sessions and engage caregivers and parents who will be part of the sessions | A team of 2 conduct group sessions
Conduct regular group sessions in workplaces and facilities | A team of 2 coaches conduct group sessions
Parent coach to conduct milestone assessment and parenting behaviour data
Supportive Supervision by Supervisors
Hold meetings with parent coaches to review performance, course correction and improve on performance
Conduct field observations and provide feedback to the parent coach | Visit each parent coach in the team and conduct field observations at least once a quarter
Consolidate monthly reports from the parent coaches conducting home visits and group sessions
Review the montoring
Conduct monitoring
Conduct quality assurance monitoring | once in 6 months quality asusrance checks with data captured into the monitoring system
Data collection

## Budget
Lusaka and Chongwe Early Childhood Development Program Initiative
Budget - Provision of Nurturing Care through Parent Coaching Program
Activity Description | Number | Qty | Unit Price | Total ZMK | Narrative
Material Development
Finalie the training materials (ECD Family Counselling cards, Group Counselling Cards, Facilitators Manaual, Participants Manual, Cards) |  |  |  | 0
Reproduction of training materials | 3050 | 1 | 50 | 152500
Vest and ID card for Parent coaches | 2000 | 1 | 350 | 700000 | 1000 IDs will cost K150 and K200 for 1000 vests/aprons
Community Engagement and Sensitization
Orientation workshop with Ward Councillors and Ward Development Committees | 1 | 1 | 194260 | 194260 | 59 wards made up of 38 wards in Lusaka and 21 wards in Chongwe participating in the one day orientation session
Hold Community Sensitization meetings using public announcement system | 24 | 1 | 24000 | 576000 | .We will also use council vehicles with PA systems and will require 560 liters for Lusaka while chongwe will require 240 liters for 3 sessions of PA
Hold thearter for development activities | 10 | 1 | 15000 | 150000 | we will conduct 7 theater for development sessions in 7 constituencies in Lusaka and 3 in Chongwe for 1 vast constituency. 5 facilitators and coaches will be included and will get a transport refund of K500
Parent Coaches and Supervisors Training |  |  |  | 0
Develop a training schedule or plan for rollout |  |  |  | 0
Conduct a resource preparatory session for parent coaching and supervisor training |  |  |  | 0
Conduct a train of trainer (TOT) session | 2 | 1 | 42500 | 85000 | This will include booking two venues, ie, Chongwe and Lusaka and some transport refund
Training of parent coaches | 25 | 1 | 40000 | 1300000 | This trraining will include training atleast 40 coaches in 25 sessions, including their transport refunds
Training of Supervisors of parent coaches | 3 | 1 | 56500 | 169500 | We will conduct 3 sessions of training atleast 35 supervisors including their transport refund
0
Conduct of Parent Coaching at Household |  |  |  | 0
Assign parent coaches to teams, supervisors and catchment areas |  |  |  | 0
Parent coaches conduct their first home visits, secure consent and enlistment (gather basic information on households) | 2 | 1 | 500000 | 1000000 | this will include transport refunds for 1000 coaches
Parent coaches conduct home visits | 2 | 1 | 500000 | 1000000 | this will include transport refunds for 1000 coaches
Parent coach to conduct milestone assessment and parenting behaviour data | 2 | 1 | 500000 | 1000000 | this will include transport refunds for 1000 coaches
Conduct of Parent Coaching at Group Level |  |  |  | 0
Identify targeted places for group sessions and engage caregivers and parents who will be part of the sessions |  |  |  | 0
Conduct regular group sessions in workplaces and facilities | 20 | 1 | 20000 | 400000 | We will conduct 20 sessions, 10 for each city and 20 coaches from each city will be involved
Parent coach to conduct milestone assessment and parenting behaviour data | 2 | 1 | 500000 | 1000000 | includes transport frefunds for the coaches
Supportive Supervision by Supervisors |  |  |  | 0
Hold meetings with parent coaches to review performance, course correction and improve on performance | 8 | 1 | 5000000 | 40000000 | these will be done quarterly in the two cities
Conduct field observations and provide feedback to the parent coach | 8 | 1 | 56500 | 452000 | will be donme quartely by the 113 supervisors and will include a transport refund
Consolidate monthly reports from the parent coaches conducting home visits and group sessions |  |  |  | 0
Review the montoring |  |  |  | 0
Conduct monitoring |  |  |  | 0
Conduct quality assurance monitoring | 4 | 1 | 28250 | 113000 | two quality assuarnce monitoring will be done by the 113 supervisors
Data collection | 4 | 1 | 28250 | 113000 | 2 surveys from each city will be conducted to highlight any good practices, assess areas of improvement and collect data for the program. The 113 supervisors will be involved in this